## Roadmap
ISMS PROJECT ROADMAP - GROUP 4
| 14.03 | 17.03 | 18.03 | 21.03 | 24.03 | 25.03 | 28.03 | 31.03 | 01.04 | 04.04 | 07.04 | 08.04
MILESTONES
Plan
Days till next step: | 3 | 1 | 3 | 3 | 1 | 3 | 3 | 1 | 3 | 3 | 1
Project Kickoff
First Review
Progress
Second Review
Making a Roadmap
DEADLINE
Facebook group chat meeting,
task 4 overview
Tasks division
Tasks
assignment for
1st review
Progress
check before
review,
early morning
Slides
and notes
overview
Task 2/5 execution
(HARD)
Task 3/5 execution
(EASY)
Task 4/5 execution
(EASY)
Task 1/5 execution
(EASY)
Task 5/5 execution
(EASY)
Progress
check before
review,
evening
Tasks
assignment for
2nd review
Tasks
assignment for
deadline
Internal review of project completeness
Corrections
Final review,
early morning